## Sheet1
November 2019 Timesheet - ED BAYUDAN
JDA-Macy's Hours | Date | Hours | Activities | Week's Hours | Week's Totals
Week 1 | 2019-11-04 | 3 | Webex on mapping sheets
| 2019-11-05 | 3 | Install Anypoint Studio, Oracle Client, other onboarding activities | 6 | 450
Week 2 | 2019-11-11 | 8 | Project overview, meetings
| 2019-11-12 | 8 | SCPO adapter flow, moreproject overview
| 2019-11-13 | 4 | Mapping sheets overview
|  | 3 | Prepare data source reqs docs and sheet
| 2019-11-14 | 2 | Review SCPO adapter flows
| 2019-11-15 | 4 | Standup, review mapping sheets recordings | 29 | 2175
Week 3 | 2019-11-18 | 2 | Webex with team on mapping sheets
|  | 2 | Attended required onboarding trainings
| 2019-11-20 | 1 | Webex with team on POC
|  | 3 | Prepare DDLs and doc for POC
| 2019-11-21 | 2 | Review Anypoint SCPO adapter flow
| 2019-11-22 | 2 | Webex with Macy's on mapping sheets
|  | 2 | Review Anypoint SCPO adapter flow | 14 | 1050
Week 4 | 2019-11-25 | 2 | Stash/Anypoint discussion with Loren/TJ
|  | 2 | Location mapping with Macys
|  | 2 | Install DB2C Express; build/test SCPO adaptor
| 2019-11-26 | 2 | Item mapping with Macys
|  | 2 | Build/test SCPO adaptor
| 2019-11-27 | 4 | Install DB2C Express and DB2 Data Studio
| 2019-11-29 | 4 | Load location schemas to DB2C; review location queries from Macys | 18 | 1350
|  | 67 | Total | 67 | 5025